## Issues
Item # | Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | Complete | System | I | Detection of wrong functional property. | Algorithm analysis, Performance analysis, Operation-concept analysis | 2016-04-13 | 2016-04-20 | 2016-05-04 | Issue resolved
2 | In progress | Module | A | Developing user interface. | Re-prototyping user interface | 2016-04-13 | 2016-05-30 | 2016-05-04 | Working on the issue
3 | New | System | I | Real time performance failure. | Simulation, remodeling, and tuning | 2016-04-20 | 2016-05-30 | 2016-05-04 | Issue resolved
4 | New | Sub-system | I | Continuing stream requirement change. | Information hiding incremental development | 2016-04-20 | 2016-05-30 | 2016-05-04 | Working on the issue
5 | In progress | Protocol | A | Scheduling issue | Scheduling estimation | 2016-04-14 | 2016-05-29 | 2016-05-04 | Issue resolved
6 | Complete | System | I | Bug in requirement | Quality factor analysis | 2016-04-25 | 2016-04-27 | 2016-05-04 | Issue resolved
7 | In progress | Service routine | A | No periodic group meeting | Group meeting | 2016-04-20 | 2016-05-30 | 2016-05-04 | Working on the issue
8 | In progress | Module | A | Resolving active problem list | Figured problem list | 2016-04-26 | 2016-05-15 | 2016-05-04 | Working on the issue
9 | Complete | Object | A | Project status documentation | Work list | 2016-04-20 | 2016-04-26 | 2016-05-04 | Issue resolved
10 | In progress | System | I | Testing phase initialization | Testing objectives | 2016-04-15 | 2016-05-15 | 2016-05-04 | Working on the issue
11 | In progress | Task | A | Main project objectives | Project objective list | 2016-04-15 | 2016-05-18 | 2016-05-04 | Working on the issue
12 | Complete | Protocol | A | Conflict between project member | Group meeting | 2016-04-10 | 2016-04-26 | 2016-05-04 | Issue resolved
13 | In progress | Module | A | Ill defined scope | General list of error in scope definition | 2016-04-26 | 2016-05-15 | 2016-05-04 | Working on the issue
14 | In progress | Module | A | Inflating scopes | Uncontrolled changes and growth of scope | 2016-04-26 | 2016-05-15 | 2016-05-04 | Working on the issue
15 | Complete | Protocol | A | Inaccuracy in time management | Inaccurate estimation of project phases | 2016-04-20 | 2016-04-21 | 2016-05-04 | Issue resolved
16 | In progress | Data model | I | Inaccuracy in dependencies | Dramatical impacts of dependencies on projects | 2016-04-26 | 2016-05-15 | 2016-05-04 | Working on the issue
17 | In progress | Module | A | Missing activities of scope | Required activity list of scope definition | 2016-04-26 | 2016-05-15 | 2016-05-04 | Issue resolved
18 | In progress | Task | A | Changing overload | Raised complexity of project for changes | 2016-04-15 | 2016-05-15 | 2016-05-04 | Working on the issue
19 | Complete | Protocol | A | Conflict over proposed changes | Source of conflicts due to change request | 2016-04-20 | 2016-05-30 | 2016-05-04 | Working on the issue
|  |  |  | Inaccurate change priorities | Prioritized non essential changes | 2016-05-01 | 2016-05-18 | 2016-05-04 | Working on the issue

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete